REMOTE PROPERTY WATCHDOG MVP Development Backlog Version 0.1 Execution-ready epics, stories, dependencies, acceptance evidence, release slices, quality gates, launch blockers, and post-MVP parking lot. Prepared for founder, product, engineering, design, QA, security, and beta operations July 13, 2026

DELIVERY OBJECTIVE Turn the approved product and architecture documents into the smallest dependable, testable, secure commercial release—without losing the product’s core promise: tell a property owner when internet, cameras, or critical monitoring equipment stop protecting the property.

# Document Control

| Field | Value |
| --- | --- |
| Document | Remote Property Watchdog — MVP Development Backlog |
| Version / status | v0.1 — execution planning and engineering estimation |
| Prepared | July 13, 2026 |
| Audience | Founder, product owner, engineering, design, QA, security, operations, and delivery partners |
| Backlog authority | Normative sequencing and acceptance baseline once approved; estimates and assignments remain planning data |
| Update cadence | At release-planning boundaries, after prototype evidence, after major scope decisions, and before each beta/launch gate |

## Version history

| Version | Date | Status | Summary |
| --- | --- | --- | --- |
| 0.1 | 2026-07-13 | Draft | Initial execution backlog derived from the approved product brief, PRD, flows, prototype specification, architecture, API specification, and security model. |

## Source documents

Founder Product Brief v0.1

Product Requirements Document v0.1

User & Incident Flow Specification v0.1

Technical Feasibility Prototype Specification v0.1

Software Architecture Blueprint v0.1

Data Model & API Specification v0.1

Security, Privacy & Threat Model v0.1

## Decision vocabulary

| Term | Meaning |
| --- | --- |
| P0 | Required for the stated release gate; missing or failed P0 work blocks that release unless explicitly descoped. |
| P1 | Important for reliability, usability, security, or commercial readiness; may be deferred only with owner and documented consequence. |
| P2 | Post-MVP enhancement or scale improvement; not part of the commercial-MVP commitment. |
| R0 | Technical feasibility prototype. |
| R1 | Internal alpha on controlled properties. |
| R2 | Private beta with selected external users. |
| R3 | Commercial MVP. |
| R4 | Post-MVP expansion. |
| XS / S / M / L / XL | Relative effort and uncertainty, not elapsed-time commitments. XL items must be split before entering implementation. |
| Acceptance evidence | Observable proof—automated test, scenario result, security review, UX validation, runbook, or artifact—not merely “code completed.” |

BACKLOG RULE A feature is not complete when its happy path works. For this product, completion also requires safe failure behavior, honest customer language, operational visibility, and evidence that outage/restoration alerts are not duplicated or silently lost.

# Document Map

| Section | Primary output |
| --- | --- |
| 1–5 | Delivery strategy, release model, prioritization, roles, and dependencies |
| 6–17 | Detailed epic backlogs with story IDs, release targets, effort, acceptance evidence, and dependencies |
| 18–23 | Release slices, build waves, readiness/Done rules, launch blockers, estimation, and governance |
| Appendix A | Master story index and release summary |
| Appendix B | Traceability from backlog epics to approved specifications |
| Appendix C | Release-gate checklists |
| Appendix D | Post-MVP parking lot and rejected/deferred scope |

HOW TO USE THIS BACKLOG Import story rows into an issue tracker using the IDs as stable keys. Preserve the acceptance evidence and dependencies. Add owner, status, estimate refinement, and implementation notes in the tracker rather than changing the product requirement implicitly.

# 1. Executive Delivery Summary

The backlog is organized around vertical customer outcomes rather than independent component completion. The critical path begins with a Windows service that records local evidence, sends authenticated heartbeats, and survives loss of internet. It then adds off-site lease detection, incident correlation, consented notifications, customer onboarding, security controls, quality validation, and commercial operations.

## 1.1 MVP outcome

COMMERCIAL MVP A homeowner can install the Windows agent, enroll one property, identify critical cameras/recorders/network devices, verify alert destinations, leave the property, receive an off-site alert when communication or a critical device fails, understand what is known versus inferred, and receive one accurate restoration message—with enough evidence and operational support to trust the service.

## 1.2 Highest-risk work

Heartbeat correctness. The cloud must detect property silence even though the property cannot report its own outage.

Classification honesty. The system must distinguish observed symptoms from likely cause and possible tampering.

Windows continuity. Sleep, reboot, crash, upgrade, and local service stop cannot silently create false confidence.

Notification reliability. Alerts need consent, deduplication, escalation, receipts, and cost controls.

Tenant and supply-chain security. A home-network agent and update path create high-consequence trust obligations.

Real-property validation. Simulation alone cannot prove behavior across Starlink, cable, DSL, routers, cameras, and Windows configurations.

## 1.3 Backlog totals

| Measure | Count / interpretation |
| --- | --- |
| Epics | 13 |
| Detailed backlog items | 130 |
| P0 items | 103 |
| P1 items | 27 |
| Release model | R0 prototype → R1 internal alpha → R2 private beta → R3 commercial MVP → R4 post-MVP |

# 2. Backlog Operating Model

## 2.1 Item hierarchy

| Level | Purpose | Completion signal |
| --- | --- | --- |
| Product outcome | Customer/business result the release must create. | Release gate passes with live demonstration and evidence. |
| Epic | Coherent capability spanning multiple components or disciplines. | All release-required stories accepted; residual risks documented. |
| Story / backlog item | Testable change with a user/system outcome. | Acceptance evidence attached and Definition of Done met. |
| Task / subtask | Implementation step owned within a story. | Contributor confirms work integrated into parent story. |
| Defect | Observed deviation from accepted requirement. | Regression added; fix verified in affected release slice. |
| Spike | Time-bounded learning needed to split or decide work. | Recommendation, evidence, and follow-up stories produced. |

## 2.2 Required tracker fields

Stable backlog ID and title

Epic and source requirement links

Priority, target release, and relative size

Owner and reviewer

Dependencies and blockers

Acceptance evidence

Security/privacy impact

Migration/rollback impact

Telemetry/support impact

Status and decision notes

## 2.3 Status model

| Status | Entry condition | Exit condition |
| --- | --- | --- |
| Proposed | Captured from approved specifications. | Product owner confirms need and release target. |
| Refine | Outcome known; details or dependency unresolved. | Definition of Ready satisfied. |
| Ready | Acceptance, dependencies, data/security impacts, and test approach known. | Implementation begins. |
| In progress | Owner actively implementing. | Code/design integrated and reviewable. |
| Verify | Implementation complete; acceptance evidence being collected. | All checks pass or defect created. |
| Accepted | Product/technical owner accepts evidence. | Eligible for release gate. |
| Blocked | External decision, dependency, or defect prevents progress. | Blocker resolved or item replanned. |
| Deferred | Explicitly removed from current release. | Re-evaluated at roadmap review. |

# 3. Release Model and Scope Boundaries

Figure 1. The product is delivered as increasingly complete vertical slices, each with an explicit exit gate.

## 3.1 Release definitions

| Release | Audience | Required outcome | Not required yet |
| --- | --- | --- | --- |
| R0 — Feasibility prototype | Founder and engineering | Always-on service, gateway/internet checks, cloud heartbeat loss, local replay, SMS outage/restoration, controlled demo. | Polished dashboard, broad discovery, billing, public support. |
| R1 — Internal alpha | Founder/team properties | Installer, discovery, critical-device checks, readiness, basic dashboard, deterministic testing, stable operation. | External onboarding polish, complete commercial controls. |
| R2 — Private beta | Small invited cohort | Guided setup, trusted contacts, escalation, incident timeline, security/privacy controls, support operations, soak evidence. | Full public scale, every camera brand, mobile apps. |
| R3 — Commercial MVP | Paying customers | Plans/billing, launch security gate, legal/customer docs, reliable support, rollback, monitoring, release evidence. | Parental controls, firewall, cloud video, broad enterprise administration. |
| R4 — Post-MVP | Validated expansion | Features prioritized from usage, reliability, support, and revenue evidence. | Anything not supported by measured demand. |

## 3.2 Non-negotiable MVP boundaries

Windows-first local agent; no macOS/Linux consumer commitment for R3.

Outbound authenticated cloud communication; no customer port forwarding.

Operational metadata by default; no cloud storage of raw surveillance video/audio.

No claim that an outage proves criminal tampering.

No firewall, parental control, antivirus, cloud recording, dispatch, or remote shell.

No requirement to support every router/camera. Unsupported checks must degrade clearly and safely.

# 4. Prioritization and Sequencing Rules

## 4.1 Priority rules

| Priority driver | Rule |
| --- | --- |
| Customer protection | Work that prevents missed, duplicate, late, or misleading alerts outranks cosmetic breadth. |
| Critical path | Foundation, agent continuity, local evidence, cloud lease, incident state, and notifications precede broad device features. |
| Trust | Tenant isolation, consent, signed updates, honest language, deletion, and diagnostics cannot be traded away for faster launch. |
| Learning | Unknowns that could invalidate the product become early spikes/prototypes, not late surprises. |
| Operations | A feature that cannot be observed, supported, rolled back, or explained is incomplete. |
| Scope discipline | When schedule/capacity is constrained, remove breadth or channels before weakening correctness and safety. |

## 4.2 Critical path

Figure 2. The simplified critical path. Cross-cutting security, quality, and operations must develop alongside the feature path.

## 4.3 Work-in-progress rules

Prefer one complete vertical slice over multiple half-integrated services.

XL stories must be split before implementation.

No new P1 feature begins while a P0 correctness/security defect blocks the same release.

Database/API changes require migration and compatibility plan before implementation.

Any feature that sends customer alerts requires a deterministic scenario test and copy review.

# 5. Team and Ownership Assumptions

The backlog does not assume a specific staffing model. One person may hold several roles, but responsibilities must remain explicit so that product acceptance, security review, and operational ownership do not disappear inside implementation.

| Role | Primary backlog responsibilities |
| --- | --- |
| Founder / Product owner | Priority, target customer, scope, alert language, pricing boundaries, acceptance of product outcomes. |
| Technical lead | Architecture integrity, dependency sequencing, ADRs, implementation quality, release recommendation. |
| Windows/agent engineer | Service, installer, probes, local data, updates, diagnostics, Windows test matrix. |
| Cloud/API engineer | Identity integration, heartbeat, ingestion, state, APIs, queues, persistence, billing integration. |
| Frontend/product designer | Onboarding, readiness, dashboard, incident comprehension, accessibility, responsive behavior. |
| QA/quality engineer | Scenario runner, failure injection, compatibility, soak, regression, release evidence. |
| Security/privacy owner | Threat model, tenant tests, secrets, supply chain, privacy controls, launch assessment. |
| Operations/support owner | Telemetry, alerts, runbooks, support tooling, incident response, backups, beta triage. |

SMALL-TEAM RULE Even with a small team, no one should self-approve every aspect of a high-risk change. Agent update, tenant authorization, notification consent, and deletion workflows require independent review before R3.

# 6. E0 — Delivery Foundation & Engineering System

EPIC OUTCOME Create a repeatable, reviewable path from source code to signed deployable artifacts without making infrastructure complexity the product.

Source traceability: Architecture §§18, 21–22; Security §§12, 17; API §§21–23.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 4 |
| P1 stories | 4 |
| Primary delivery releases | R0, R1, R2 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| DEL-001 | P0 / R0 / S | Create source repositories and protected main branch with required review. | Branch protection active; pull request template captures tests, security, migration, and rollback impact. | — |
| DEL-002 | P0 / R0 / M | Establish local, test, staging, and production configuration boundaries. | No production secrets in source; environment-specific settings documented and validated at startup. | DEL-001 |
| DEL-003 | P0 / R0 / M | Build CI pipeline for compile, unit tests, linting, dependency scan, and artifact publication. | A clean commit produces traceable artifacts; failed checks block merge. | DEL-001 |
| DEL-004 | P0 / R0 / M | Create database migration workflow for cloud and local schemas. | Forward migration and rollback/restore procedure tested on representative data. | DEL-002 |
| DEL-005 | P1 / R1 / S | Introduce feature flags and environment-scoped rollout controls. | Incomplete or risky behavior can be disabled without reinstalling every agent. | DEL-002 |
| DEL-006 | P1 / R1 / S | Adopt coding, logging, error-handling, and API review standards. | Standards published; sample pull request passes checklist. | DEL-001 |
| DEL-007 | P1 / R1 / S | Create Architecture Decision Record workflow and initial ADR register. | Material technical decisions have owner, context, decision, consequences, and status. | DEL-001 |
| DEL-008 | P1 / R2 / M | Create signed release manifest and artifact provenance process. | Every beta artifact maps to source revision, build record, signature, SBOM, and release notes. | DEL-003, SEC-007 |

## E0 epic acceptance gate

A clean source revision produces traceable, reviewed artifacts.

Environment and schema changes are repeatable and rollback-aware.

Release provenance and decision records exist before external beta.

# 7. E1 — Windows Agent Runtime, Installation & Lifecycle

EPIC OUTCOME Deliver a dependable always-on Windows service that survives normal restarts, exposes readiness, and fails visibly rather than silently.

Source traceability: Prototype §§6, 14; Architecture §§5, 19; Security §8.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 7 |
| P1 stories | 3 |
| Primary delivery releases | R0, R1, R2 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| AGT-001 | P0 / R0 / M | Implement Windows service host with structured startup, shutdown, and health state. | Service starts on supported Windows versions; state transitions and fatal startup reasons are logged. | DEL-003 |
| AGT-002 | P0 / R0 / M | Create install, repair, upgrade, and uninstall package. | Fresh install and clean uninstall pass automated VM test; user data removal behavior is explicit. | AGT-001 |
| AGT-003 | P0 / R0 / S | Configure automatic startup and bounded service recovery after crash. | Crash test causes controlled restart; repeated failure stops restart loop and becomes observable. | AGT-001 |
| AGT-004 | P0 / R1 / M | Implement local readiness/status interface for service, cloud, gateway, and monitoring state. | Customer can see active/degraded/not-ready reason without administrator tools. | AGT-001, CLD-003 |
| AGT-005 | P0 / R1 / M | Detect sleep/hibernation risk and guide the customer to an always-on configuration. | Readiness check identifies incompatible power plan and records acknowledged override. | AGT-004 |
| AGT-006 | P0 / R1 / M | Implement agent registration and secure credential bootstrap. | One-time enrollment binds agent to property; bootstrap secret cannot be reused. | CLD-002, SEC-003 |
| AGT-007 | P0 / R1 / M | Implement versioned configuration cache with transactional apply and last-known-good rollback. | Invalid config is rejected; previous working config remains active; result is reported. | CLD-006, DAT-001 |
| AGT-008 | P1 / R2 / M | Implement staged, signed, rollback-capable automatic updates. | Signature failure blocks install; canary rollout and rollback are demonstrated. | DEL-008, SEC-007 |
| AGT-009 | P1 / R2 / S | Provide privacy-safe diagnostic bundle generation. | Bundle inventory is previewable; secrets/raw credentials excluded; export is audited locally. | OPS-005, SEC-008 |
| AGT-010 | P1 / R2 / S | Enforce CPU, memory, concurrency, and network-rate guardrails. | Soak test remains within approved resource envelope and probe rate limits. | MON-010, QA-006 |

## E1 epic acceptance gate

Service survives reboot/crash and exposes why it is not monitoring.

Install, upgrade, rollback, and uninstall are tested on the supported Windows matrix.

The agent cannot silently claim protection while sleeping or unregistered.

# 8. E2 — Local Persistence, Outbox & Offline Reconciliation

EPIC OUTCOME Preserve evidence during outages and replay it deterministically after recovery without duplication, corruption, or misleading timestamps.

Source traceability: Prototype §8; Architecture §§5.5, 8; API §8; Security §8.4.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 7 |
| P1 stories | 2 |
| Primary delivery releases | R0, R1, R2 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| DAT-001 | P0 / R0 / M | Create versioned local SQLite schema for state, probe samples, events, config, and outbox. | Schema initializes idempotently; integrity checks pass after restart. | DEL-004 |
| DAT-002 | P0 / R0 / M | Implement transaction boundaries and crash-safe journal settings. | Power/crash injection produces no partial state transition or unrecoverable database. | DAT-001 |
| DAT-003 | P0 / R0 / M | Implement durable outbox for material events and heartbeat-adjacent evidence. | Cloud-unavailable test queues events; reconnect drains in order without loss. | DAT-001, CLD-005 |
| DAT-004 | P0 / R0 / S | Assign stable event IDs and monotonic agent sequence numbers. | Duplicate replay is accepted idempotently; ordering conflicts are detectable. | DAT-003 |
| DAT-005 | P0 / R1 / M | Implement reconciliation and cloud acknowledgment checkpoints. | Agent resumes from last acknowledged sequence after restart or partial upload. | DAT-003, CLD-005 |
| DAT-006 | P0 / R1 / S | Implement UTC time handling, clock-skew detection, and observed-versus-received timestamps. | Clock rollback/advance test does not reorder evidence silently. | DAT-004 |
| DAT-007 | P1 / R2 / S | Implement bounded local retention, compaction, and disk-pressure behavior. | Retention policy removes eligible detail but preserves unresolved incident evidence; low disk is visible. | DAT-001 |
| DAT-008 | P0 / R1 / M | Protect local secrets using Windows-bound secure storage and strict ACLs. | Credential material is unreadable from ordinary config/database exports and absent from logs. | SEC-003 |
| DAT-009 | P1 / R2 / S | Create local backup/recovery procedure for configuration and durable evidence. | Corrupt-database simulation enters safe degraded mode and supports controlled recovery. | DAT-002, OPS-007 |

## E2 epic acceptance gate

Outage evidence survives loss of cloud connectivity and agent restart.

Replay is ordered, idempotent, and clock anomalies are explicit.

Secrets and unresolved incident evidence are protected under retention/disk pressure.

# 9. E3 — Network Discovery, Device Identity & Health Monitoring

EPIC OUTCOME Identify the property’s critical connectivity chain and collect enough independent evidence to distinguish broad outages from isolated device failures.

Source traceability: PRD §§6.2–6.5; Prototype §7; Architecture §12.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 9 |
| P1 stories | 3 |
| Primary delivery releases | R0, R1, R2 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| MON-001 | P0 / R0 / S | Identify active gateway and primary local interface. | Works on Ethernet/Wi-Fi test networks; interface change updates state without restart. | AGT-001 |
| MON-002 | P0 / R0 / M | Implement independent internet checks using multiple destinations and methods. | One provider/DNS failure does not falsely declare total internet loss; timeouts are bounded. | MON-001 |
| MON-003 | P0 / R0 / S | Implement explicit DNS resolution health check. | DNS-only failure is distinguishable from gateway and general internet failure. | MON-002 |
| MON-004 | P0 / R1 / L | Discover LAN devices using safe bounded methods and merge observations into inventory. | Representative router, camera, DVR, hub, phone, and PC are found without disruptive scan rate. | MON-001, DAT-001 |
| MON-005 | P0 / R1 / M | Create durable device identity evidence across changing IP addresses. | Known device changing IP remains one device when evidence supports match; ambiguity is exposed. | MON-004 |
| MON-006 | P0 / R1 / M | Allow customer to create monitor targets and choose appropriate reachability/service checks. | Critical device can be monitored without assuming ping support; invalid endpoint is explained. | MON-004, UX-005 |
| MON-007 | P0 / R1 / M | Implement TCP/service reachability probes with deadlines and response bounds. | Service-up/device-up distinctions are recorded; malformed response cannot crash agent. | AGT-010 |
| MON-008 | P1 / R2 / M | Recognize probable cameras, recorders, hubs, and infrastructure using evidence-based labels. | Classification shows confidence/source and permits customer correction. | MON-004 |
| MON-009 | P1 / R2 / L | Prototype RTSP session/frame-freshness check without storing media content. | Supported test cameras produce stream-healthy/failed evidence; credentials remain local. | MON-007, DAT-008 |
| MON-010 | P0 / R1 / M | Implement baselines, confirmation windows, flapping suppression, and cooldowns. | Brief packet loss does not create incident flood; sustained failure still meets detection target. | MON-002, MON-006 |
| MON-011 | P0 / R2 / M | Model dependency chain among internet, gateway, switch/hub, recorder, and cameras. | Incident view can identify upstream shared dependency from configured/evidenced relationships. | MON-005, UX-005 |
| MON-012 | P1 / R2 / S | Generate new-device and identity-change events with customer controls. | Known rediscovery is not treated as new; alert can be disabled independently from critical-device alerts. | MON-004, INC-001 |

## E3 epic acceptance gate

Independent checks separate gateway, DNS, internet, device, and service failure.

Probe behavior is bounded and non-disruptive.

Critical devices can be identified and monitored without depending on one protocol.

# 10. E4 — Cloud Control Plane, Heartbeats & Configuration

EPIC OUTCOME Provide authoritative off-site detection when the property stops communicating while keeping ingestion idempotent, tenant-scoped, and operationally simple.

Source traceability: Prototype §§9–10; Architecture §6; API §§14–17.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 8 |
| P1 stories | 2 |
| Primary delivery releases | R0, R1, R2 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| CLD-001 | P0 / R0 / M | Implement organization, user, property, and agent persistence baseline. | Entities enforce ownership and lifecycle invariants; migrations are repeatable. | DEL-004 |
| CLD-002 | P0 / R0 / M | Implement one-time agent registration endpoint and credential issuance. | Token is single-use, expires, binds agent to property, and is auditable. | CLD-001, SEC-002 |
| CLD-003 | P0 / R0 / M | Implement authenticated heartbeat ingestion with server receive timestamp. | Valid heartbeat renews lease; invalid/foreign agent is rejected without data leak. | CLD-002 |
| CLD-004 | P0 / R0 / L | Implement heartbeat lease evaluator and property-silence state machine. | Missed-heartbeat scenario opens one incident at threshold and avoids duplicate opens. | CLD-003 |
| CLD-005 | P0 / R0 / L | Implement idempotent batch event ingestion and acknowledgment. | Duplicate and partially retried batches do not duplicate evidence or incidents. | DAT-003, DAT-004 |
| CLD-006 | P0 / R1 / M | Implement versioned configuration snapshot/delta delivery. | Agent receives only own property config; ETag/version mismatch is handled predictably. | CLD-001, AGT-007 |
| CLD-007 | P1 / R2 / M | Implement bounded command queue for safe agent actions such as refresh/test. | Commands are capability-scoped, expire, are acknowledged, and cannot become remote shell. | CLD-002, SEC-005 |
| CLD-008 | P0 / R1 / M | Implement customer API conventions, errors, pagination, idempotency, and rate limits. | Contract tests cover standard envelope, error codes, retry semantics, and tenant denial. | CLD-001 |
| CLD-009 | P0 / R1 / M | Create dashboard read projections for property, agent, device, and incident status. | Current state can be loaded without replaying full event history. | CLD-003, CLD-005 |
| CLD-010 | P1 / R2 / M | Add background-job framework with tenant context, retries, and dead-letter visibility. | Failed job is observable and replayable; duplicate execution remains safe. | CLD-005, OPS-001 |

## E4 epic acceptance gate

Cloud detects missed heartbeats and accepts replay without duplicates.

Every request is authenticated and property-scoped.

Configuration and jobs are versioned, bounded, and observable.

# 11. E5 — Incident Classification, Correlation & Evidence

EPIC OUTCOME Convert raw failures into a small set of honest, explainable incidents with confidence, evidence, lifecycle, and restoration behavior.

Source traceability: PRD §§7–9; Flows §§5–14; Architecture §10; API §11.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 9 |
| P1 stories | 2 |
| Primary delivery releases | R0, R1, R2 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| INC-001 | P0 / R0 / M | Implement canonical device/target health state machine. | Unknown, healthy, suspected, offline, recovering, and suppressed transitions are deterministic. | MON-006 |
| INC-002 | P0 / R0 / M | Classify property silence from cloud lease expiry without overclaiming cause. | Message states communication stopped and lists plausible causes; no claim of sabotage. | CLD-004 |
| INC-003 | P0 / R0 / M | Classify local gateway, DNS, and internet failure combinations. | Controlled scenarios yield expected class and evidence summary. | MON-001, MON-002, MON-003 |
| INC-004 | P0 / R1 / M | Classify isolated critical-device/service failure while upstream path remains healthy. | One camera/DVR failure produces one scoped incident with unaffected context. | INC-001, MON-006 |
| INC-005 | P0 / R1 / M | Correlate simultaneous multi-device failures into likely shared-dependency incident. | No alert storm; child device symptoms attach to parent incident. | MON-011, INC-004 |
| INC-006 | P1 / R2 / L | Detect unusual sequential critical-device failures as a pattern, not a criminal conclusion. | Pattern threshold is configurable/tested; alert says unusual/possible disconnection. | INC-004, INC-005 |
| INC-007 | P0 / R1 / M | Assign evidence-based confidence and reason codes. | Every classification exposes supporting/contradicting evidence and confidence level. | INC-002–005 |
| INC-008 | P0 / R1 / M | Implement incident open, update, acknowledge, restore, close, and revise lifecycle. | Transitions are idempotent, timestamped, audited, and visible to dashboard/notifications. | CLD-005, INC-007 |
| INC-009 | P0 / R1 / M | Correlate restoration evidence and calculate downtime without hiding uncertainty. | Restoration sends once; delayed evidence can revise timeline while retaining history. | INC-008, DAT-006 |
| INC-010 | P0 / R2 / M | Build customer-safe evidence timeline projection. | Timeline shows observations, system inference, notification delivery, acknowledgment, and recovery separately. | INC-008, CLD-009 |
| INC-011 | P1 / R2 / S | Support planned maintenance/suppression without erasing evidence. | Maintenance prevents escalation but records expected downtime and expiration. | INC-008, UX-010 |

## E5 epic acceptance gate

Controlled scenarios produce the expected incident class, confidence, and evidence.

One underlying outage does not create a flood of unrelated incidents.

Restoration and later revisions preserve history and uncertainty.

# 12. E6 — Notifications, Trusted Contacts & Escalation

EPIC OUTCOME Deliver concise, consented, deduplicated alerts through dependable channels while controlling cost, abuse, and message fatigue.

Source traceability: PRD §6.8; Flows §§9–13; Architecture §11; Security §11.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 7 |
| P1 stories | 3 |
| Primary delivery releases | R0, R1, R2 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| NTF-001 | P0 / R0 / M | Create versioned template system for open, update, restore, test, and uncertainty messages. | Templates require incident class, severity, property label, time, and safe action; snapshot tested. | INC-002 |
| NTF-002 | P0 / R0 / M | Implement transactional email delivery and provider receipt processing. | Test and incident email produce queued/sent/delivered/failed status. | NTF-001 |
| NTF-003 | P0 / R0 / M | Implement SMS delivery with verified consent, STOP handling, quotas, and receipts. | Only verified opted-in destination receives SMS; opt-out prevents future sends. | NTF-001, SEC-010 |
| NTF-004 | P0 / R1 / M | Implement per-incident deduplication, cooldown, and alert-flood suppression. | Repeated evidence updates do not send duplicate open alerts; delivery remains traceable. | INC-008 |
| NTF-005 | P0 / R1 / M | Create trusted-contact enrollment, verification, role, and removal lifecycle. | Contact can verify/decline; owner can revoke; destination changes require re-verification. | UX-006, SEC-010 |
| NTF-006 | P0 / R1 / L | Implement escalation policies by severity, channel, delay, and unresolved duration. | Deterministic test clock produces expected sequence and stops after acknowledgment/restoration. | NTF-002, NTF-003, INC-008 |
| NTF-007 | P1 / R2 / S | Implement quiet hours with emergency-severity override. | Noncritical alert defers; critical policy behavior is explicit and testable. | NTF-006 |
| NTF-008 | P0 / R1 / S | Implement end-to-end notification test from each configured property. | Customer sees actual delivery outcome before monitoring is declared ready. | NTF-002, NTF-003, UX-007 |
| NTF-009 | P1 / R2 / M | Add mobile/web push channel behind channel abstraction. | Push can be enabled without changing incident engine or existing delivery records. | NTF-006 |
| NTF-010 | P1 / R2 / S | Expose quota use, provider delay, and destination failure to customer/support. | Customer is not shown “sent” when provider failed; quota exhaustion has safe fallback. | BIL-002, OPS-005 |

## E6 epic acceptance gate

Only consented destinations receive alerts.

Open/update/restore messages are deduplicated and delivery state is truthful.

Escalation stops correctly on acknowledgment or restoration.

# 13. E7 — Customer Onboarding, Dashboard & Incident Experience

EPIC OUTCOME Make a technically complex monitoring system understandable to a homeowner and prevent “protected” status until the system is actually ready.

Source traceability: PRD §9; User Flows §§1–18; Architecture §7.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 11 |
| P1 stories | 1 |
| Primary delivery releases | R1, R2 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| UX-001 | P0 / R1 / M | Implement account creation, sign-in, password recovery, and session management. | Customer can securely access dashboard; authentication errors reveal no account existence. | SEC-002 |
| UX-002 | P0 / R1 / S | Implement property creation with timezone, label, and monitoring purpose. | Property is isolated to organization and uses timezone only for presentation/schedules. | CLD-001 |
| UX-003 | P0 / R1 / L | Create guided agent enrollment and installer handoff flow. | User receives single-use enrollment path and sees agent check in successfully. | AGT-006, CLD-002 |
| UX-004 | P0 / R1 / L | Create discovery review flow with names, types, confidence, and corrections. | User can distinguish recognized, ambiguous, and ignored devices without IP expertise. | MON-004, MON-008 |
| UX-005 | P0 / R1 / M | Create critical-device selection and dependency-chain setup. | User marks camera/DVR/router/hub critical and sees checks to be used. | MON-006, MON-011 |
| UX-006 | P0 / R1 / M | Create notification destination, trusted contact, and escalation setup. | Verification and consent status are visible; invalid destination blocks readiness. | NTF-005, NTF-006 |
| UX-007 | P0 / R1 / M | Implement readiness checklist and protection-state model. | Protected state requires agent active, monitoring configured, and at least one tested channel. | AGT-004, NTF-008 |
| UX-008 | P0 / R1 / M | Build responsive property status dashboard. | Shows internet, agent, critical devices, active incidents, and last confirmed healthy time. | CLD-009 |
| UX-009 | P0 / R2 / L | Build incident detail and evidence timeline with acknowledgment. | Customer can understand what is known, inferred, unresolved, notified, and restored. | INC-010 |
| UX-010 | P0 / R2 / M | Implement Away/Tamper Mode and planned-maintenance controls. | Mode change is audited; faster policy applies; maintenance automatically expires. | INC-011, NTF-006 |
| UX-011 | P1 / R2 / M | Provide uptime/outage report and export. | Date range produces consistent downtime totals and incident links. | INC-009 |
| UX-012 | P0 / R2 / S | Meet responsive and accessibility baseline for critical workflows. | Keyboard, labels, contrast, error association, and mobile layouts pass defined audit. | QA-009 |

## E7 epic acceptance gate

A nontechnical customer can become genuinely ready without IP/network expertise.

The dashboard distinguishes current state, last known state, and uncertainty.

Critical flows work on mobile and with keyboard/screen-reader basics.

# 14. E8 — Security, Privacy, Identity & Supply Chain

EPIC OUTCOME Enforce the product’s trust promises as release gates, not optional hardening after customers are connected.

Source traceability: Security Model §§8–22; Architecture §§13–14; API §20.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 11 |
| P1 stories | 1 |
| Primary delivery releases | R0, R1, R2, R3 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| SEC-001 | P0 / R0 / S | Adopt threat model, data classes, trust boundaries, and secure coding checklist. | Team review completed; high-risk changes require threat-model update. | DEL-006 |
| SEC-002 | P0 / R1 / M | Implement managed human identity with secure sessions and MFA-ready design. | Session expiry/revocation works; sensitive account changes require recent authentication. | UX-001 |
| SEC-003 | P0 / R0 / M | Implement per-agent identity, protected credentials, rotation, and revocation. | Compromised agent credential can be revoked without affecting other properties. | CLD-002, DAT-008 |
| SEC-004 | P0 / R0 / S | Enforce TLS, certificate validation, secure headers, and secret-free logs. | Transport tests reject invalid cert; automated scan finds no plaintext secret logging. | CLD-003 |
| SEC-005 | P0 / R1 / M | Implement server-side RBAC and property authorization. | Negative tests prove guessed IDs and foreign agents cannot access another property. | CLD-001, CLD-008 |
| SEC-006 | P0 / R1 / M | Create automated cross-tenant and IDOR regression suite. | Suite covers customer, worker, agent, export, and support paths and blocks release on failure. | SEC-005, QA-002 |
| SEC-007 | P0 / R2 / L | Implement code signing, SBOM, dependency policy, update signing, and protected release keys. | Unsigned/tampered installer or update is rejected; key access is audited. | DEL-008, AGT-008 |
| SEC-008 | P0 / R1 / M | Implement logging/data-minimization rules and sensitive-field redaction. | Fixtures containing secrets/PII do not appear in logs, support bundle, or telemetry. | OPS-001 |
| SEC-009 | P0 / R2 / M | Implement customer export, retention, property deletion, and account deletion workflows. | Deletion state machine removes eligible data and documents lawful/operational exceptions. | DAT-007, CLD-001 |
| SEC-010 | P0 / R0 / M | Implement messaging consent, destination verification, throttling, and abuse controls. | Unverified/opted-out numbers cannot be messaged; repeated verification is rate-limited. | NTF-003 |
| SEC-011 | P1 / R2 / M | Add SAST, dependency, secret, container/IaC, and dynamic security scanning. | Critical finding blocks release or has documented risk acceptance and deadline. | DEL-003 |
| SEC-012 | P0 / R3 / L | Complete independent pre-launch security assessment and remediate launch blockers. | Scope covers agent, cloud, API, dashboard, tenancy, update path, and notifications. | SEC-006, SEC-007, QA-010 |

## E8 epic acceptance gate

Cross-tenant access tests pass and update artifacts are trusted.

Data collection, retention, support access, and messaging consent match published promises.

No unresolved critical security finding remains at public launch.

# 15. E9 — Plans, Entitlements, Billing & Administrative Controls

EPIC OUTCOME Support a sustainable subscription without allowing billing logic to weaken monitoring correctness or strand customers during outages.

Source traceability: Architecture §20; API §§10, 16.6; PRD §6.11.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 5 |
| P1 stories | 1 |
| Primary delivery releases | R2, R3 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| BIL-001 | P0 / R2 / M | Define plan/entitlement model separate from payment provider. | Feature checks use internal entitlements; provider outage does not stop active monitoring. | CLD-001 |
| BIL-002 | P0 / R2 / M | Implement quotas for properties, critical devices, SMS, contacts, and retention. | Quota decisions are atomic, visible, auditable, and do not silently drop critical alerts. | BIL-001 |
| BIL-003 | P0 / R3 / L | Integrate subscription checkout, renewal, cancellation, and webhook validation. | Signed provider events update internal subscription idempotently; replay is safe. | BIL-001, SEC-004 |
| BIL-004 | P0 / R2 / M | Meter SMS and other billable usage with reconciliation. | Provider totals can be reconciled to internal usage and customer quota. | NTF-003, BIL-002 |
| BIL-005 | P1 / R3 / S | Implement grace period, downgrade, and cancellation behavior. | Customer is warned; data/monitoring behavior is explicit; no surprise immediate security blackout. | BIL-001 |
| BIL-006 | P0 / R2 / M | Implement audited support/admin controls for plan corrections and account recovery. | High-risk action requires role, reason, and audit record; no unrestricted impersonation. | OPS-005, SEC-005 |

## E9 epic acceptance gate

Entitlements are independent of payment-provider availability.

Quota/billing behavior never silently discards a critical alert.

Support/billing corrections are constrained and audited.

# 16. E10 — Quality Engineering, Failure Injection & Release Validation

EPIC OUTCOME Prove the product under the same failures it claims to detect: unplugged devices, severed internet, process crashes, sleep, clock changes, reconnect storms, and provider outages.

Source traceability: Prototype §§16–20; Security §21; Architecture §25.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 9 |
| P1 stories | 1 |
| Primary delivery releases | R0, R1, R2, R3 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| QA-001 | P0 / R0 / M | Establish unit-test baseline for state machines, probe decisions, templates, and validation. | Critical modules meet agreed coverage and mutation/edge-case expectations. | DEL-003 |
| QA-002 | P0 / R0 / L | Create cloud/agent integration environment with disposable data and fake providers. | Registration, heartbeat, event replay, incident, and notification path runs automatically. | CLD-005, NTF-001 |
| QA-003 | P0 / R0 / L | Build deterministic scenario runner with virtual clock and scripted evidence. | Core incident matrix executes repeatably without waiting in real time. | INC-003, NTF-006 |
| QA-004 | P0 / R1 / M | Create physical failure-injection checklist and evidence-capture template. | Tests include cable/device unplug, gateway loss, internet loss, service stop, sleep, reboot, restore. | QA-003 |
| QA-005 | P0 / R1 / M | Automate Windows compatibility tests across supported editions/updates. | Install, service, upgrade, sleep readiness, and uninstall pass on defined matrix. | AGT-002 |
| QA-006 | P0 / R2 / L | Run long-duration agent/cloud soak with network churn and intermittent provider failure. | No unbounded memory/disk growth, event loss, alert storm, or stuck incident. | AGT-010, DAT-007 |
| QA-007 | P0 / R2 / L | Run fault-injection tests for database, queue, messaging, auth, clock, and restart failures. | System enters documented degraded mode and recovers without cross-property impact. | OPS-007 |
| QA-008 | P1 / R2 / M | Validate heartbeat/reconnect-storm performance and notification throughput. | Load target met with bounded latency and no duplicate incidents/alerts. | CLD-004, OPS-002 |
| QA-009 | P0 / R2 / M | Perform accessibility and responsive UX audit on critical flows. | Defined WCAG-aligned checklist passes for onboarding, status, incident, and contacts. | UX-012 |
| QA-010 | P0 / R3 / L | Create signed release regression suite and launch evidence package. | All P0 stories trace to passing tests; known defects and risk acceptances are approved. | All P0 |

## E10 epic acceptance gate

The full incident matrix runs deterministically and on real equipment.

Soak/fault tests show no event loss, duplicate alert storm, or unrecoverable state.

Every P0 story has release evidence.

# 17. E11 — Observability, Support Operations & Recovery

EPIC OUTCOME Give operators enough visibility to detect platform failures, assist customers without privacy overreach, and recover safely from provider or data-system problems.

Source traceability: Architecture §§15, 17–18; Security §§16, 18–19.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 8 |
| P1 stories | 2 |
| Primary delivery releases | R0, R1, R2, R3 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| OPS-001 | P0 / R0 / M | Implement structured logs with correlation IDs, tenant-safe fields, and redaction. | Incident path is traceable; secrets and raw camera credentials are absent. | SEC-008 |
| OPS-002 | P0 / R1 / L | Create service dashboards for heartbeat freshness, incident rates, queues, provider outcomes, and errors. | Operator can distinguish customer outage spike from platform failure. | CLD-003, NTF-002 |
| OPS-003 | P0 / R1 / M | Configure operational alerts with runbook links and anti-noise thresholds. | Simulated service/provider failure pages correct owner with actionable context. | OPS-002 |
| OPS-004 | P0 / R1 / M | Implement immutable audit events for security, support, contacts, billing, and configuration. | Sensitive change records actor, target, before/after summary, reason, and time. | SEC-005 |
| OPS-005 | P0 / R2 / L | Build restricted support console and privacy-safe diagnostic workflow. | Support can inspect status/evidence metadata without viewing secrets or unrelated tenant data. | AGT-009, OPS-004 |
| OPS-006 | P1 / R3 / S | Publish service status and customer communication workflow. | Major cloud/provider incident can be acknowledged without triggering misleading property alerts. | OPS-003 |
| OPS-007 | P0 / R2 / L | Implement backup, restore, queue replay, and disaster-recovery exercises. | Restore meets approved data-loss/recovery objectives and tenant integrity checks. | CLD-001, DAT-009 |
| OPS-008 | P0 / R2 / M | Create security/availability incident response playbooks and contact tree. | Tabletop exercise completes; decisions, communications, and evidence owners are clear. | SEC-001 |
| OPS-009 | P1 / R3 / M | Define messaging-provider degradation/fallback behavior. | Queued/delayed/failed state is visible; alternate channel can be used without duplicates. | NTF-002, NTF-003 |
| OPS-010 | P0 / R2 / S | Create beta support triage, defect severity, and escalation process. | Customer report maps to incident/session evidence and receives traceable disposition. | OPS-005 |

## E11 epic acceptance gate

Operators can distinguish property incidents from platform incidents.

Backups, restores, provider failures, and support access are exercised.

Customer support can diagnose common issues without privacy overreach.

# 18. E12 — Beta, Commercial Readiness & Launch Management

EPIC OUTCOME Validate reliability and value with real properties, then launch only when the product can be supported, explained, rolled back, and sold responsibly.

Source traceability: PRD §§13–16; Prototype §§19–20; Security §22.

| Release-critical profile | Value |
| --- | --- |
| P0 stories | 8 |
| P1 stories | 2 |
| Primary delivery releases | R1, R2, R3, R4 |
| Acceptance focus | Working behavior, safe failure, tests, observability, and documentation |

| ID | P / Rel. / Size | Backlog item | Acceptance evidence | Depends |
| --- | --- | --- | --- | --- |
| REL-001 | P0 / R1 / S | Define internal-alpha properties, hardware/network diversity, and test owners. | Each property has documented topology, critical devices, expected failures, and rollback contact. | QA-004 |
| REL-002 | P0 / R2 / M | Create private-beta enrollment, informed consent, eligibility, and support expectations. | Participant understands software-only limitations and how data/alerts are handled. | SEC-009, OPS-010 |
| REL-003 | P0 / R2 / M | Instrument product success metrics and beta feedback loop. | False-alert, missed-alert, setup completion, notification delivery, retention, and support burden are reviewed. | OPS-002 |
| REL-004 | P0 / R2 / M | Create customer help center, onboarding guide, troubleshooting, and limitations copy. | User can resolve common sleep, firewall, device-identity, and delivery issues. | UX-007, OPS-010 |
| REL-005 | P0 / R3 / M | Prepare terms, privacy notice, messaging disclosures, acceptable use, and billing disclosures for counsel review. | Product behavior and data practices match published documents; unresolved legal questions block launch. | SEC-009, SEC-010, BIL-003 |
| REL-006 | P0 / R3 / M | Finalize packaging, plans, trial/grace rules, and customer-facing positioning. | Plan limits match entitlement implementation and do not promise unsupported diagnosis. | BIL-001–005 |
| REL-007 | P0 / R3 / L | Execute commercial-MVP launch readiness review. | All launch blockers closed or formally accepted; rollback, support, monitoring, and communications verified. | QA-010, SEC-012, OPS-007 |
| REL-008 | P0 / R3 / S | Create release rollback, pause-enrollment, and emergency notification procedures. | Team can stop rollout, revoke bad update, disable channel, and communicate status. | AGT-008, OPS-008 |
| REL-009 | P1 / R3 / S | Publish release notes and known limitations in customer-safe language. | No claim exceeds verified capability; material limitations are prominent. | REL-007 |
| REL-010 | P1 / R4 / S | Run post-launch review and re-prioritize parking lot from evidence. | Roadmap decision cites product metrics, support demand, reliability, and revenue—not feature enthusiasm alone. | REL-003 |

## E12 epic acceptance gate

Beta participants and limitations are managed explicitly.

Commercial claims match tested behavior and entitlements.

Launch can be paused or rolled back safely.

# 18. Release Slices and Minimum Demonstrable Increments

| Slice | End-to-end demonstration | Stories that dominate the slice |
| --- | --- | --- |
| Slice A — Heartbeat proof | Agent service sends heartbeats; cloud detects silence; SMS opens/restores; local evidence replays. | AGT-001–003, DAT-001–004, CLD-002–005, INC-002–003, NTF-001–003, QA-001–003 |
| Slice B — Critical-device proof | Customer selects a camera/DVR/device; isolated unplug produces scoped incident; internet remains healthy. | MON-004–007, MON-010, INC-001/004, UX-004/005, NTF-004/008 |
| Slice C — Shared outage proof | Gateway/internet/shared dependency failure creates one correlated incident and one restoration. | MON-011, INC-005/007–009, UX-008/009, QA-004 |
| Slice D — Trustworthy beta | Installer/readiness, contacts/escalation, privacy/security, diagnostics, support and soak evidence. | AGT-004–010, UX-003–012, SEC P0, OPS P0, QA-005–009, REL-001–004 |
| Slice E — Commercial MVP | Billing/entitlements, legal/customer materials, independent security review, launch regression and rollback. | BIL P0, SEC-012, QA-010, REL-005–009 |

SLICE ACCEPTANCE Every slice must be deployable in a controlled environment and demonstrate the customer outcome through the real agent/cloud/notification path. Mocks may support automated tests but cannot be the only acceptance evidence.

# 19. Indicative Build Waves

These waves express dependency order, not a promise of calendar duration. Parallel work is appropriate only when interfaces and acceptance evidence are stable enough to avoid rework.

| Wave | Primary focus | Exit signal |
| --- | --- | --- |
| Wave 0 — Decisions and foundation | Resolve key open choices; repositories, environments, CI, schemas, threat model adoption. | Team can build and deploy a minimal agent/cloud change reproducibly. |
| Wave 1 — Core heartbeat vertical | Windows service, local journal/outbox, registration, heartbeat lease, email/SMS, scenario runner. | R0 feasibility demo passes repeatedly. |
| Wave 2 — Monitoring and state | Gateway/DNS/internet, discovery, critical targets, device state, dedupe, basic status. | Founder property runs continuously with intelligible incidents. |
| Wave 3 — Customer setup | Installer hardening, guided enrollment, device review, contacts, readiness, dashboard. | A new internal user can set up without engineer intervention. |
| Wave 4 — Correlation and evidence | Dependencies, multi-device incidents, confidence, timeline, restoration, maintenance. | Controlled failure matrix produces expected incident set and language. |
| Wave 5 — Beta hardening | Security/tenancy, signed updates, consent, privacy lifecycle, soak/fault tests, support tools. | R2 private-beta gates pass. |
| Wave 6 — Commercial controls | Plans, quotas, billing, legal/customer copy, independent assessment, launch regression. | R3 launch review can make an evidence-based go/no-go decision. |

# 20. Definition of Ready and Definition of Done

Figure 3. A story reaches release only after implementation, verification, observability, acceptance, and release controls are complete.

## 20.1 Definition of Ready

Outcome and user/system value are unambiguous.

Target release and priority are assigned.

Dependencies, data changes, API changes, and migration needs are known.

Acceptance evidence can be produced in a test environment.

Failure and restoration behavior are specified.

Security/privacy/consent impact is assessed.

Alerting copy or UX state is reviewed where applicable.

Item is small enough to complete without hiding multiple unrelated outcomes.

## 20.2 Definition of Done

Implementation reviewed and integrated behind appropriate rollout controls.

Automated tests pass; deterministic incident scenario added when behavior affects monitoring/alerts.

Manual/physical validation completed where simulation is insufficient.

Logs, metrics, audit, support, and error states are implemented.

Security/privacy requirements and negative authorization tests pass.

Migration, compatibility, and rollback behavior tested.

Customer/help/runbook documentation updated.

Acceptance evidence attached and product/technical owner accepts outcome.

# 21. Launch Blockers and Cut Rules

## 21.1 Automatic R3 blockers

| Blocker | Why it blocks commercial launch |
| --- | --- |
| Missed or duplicate critical alert in a supported controlled scenario | Invalidates the central paid promise. |
| Heartbeat lease opens/restores incidents incorrectly under reconnect/retry conditions | Can create false security emergencies or hide real outages. |
| Cross-tenant data access or agent/property binding flaw | High-consequence privacy and security failure. |
| Unsigned/untrusted agent update path or unsafe rollback | Compromise could reach customer home networks. |
| Unverified/opted-out SMS destination receives messages | Consent, abuse, and regulatory risk. |
| Agent can show “protected” while sleeping, stopped, unregistered, or notification test failed | Creates dangerous false confidence. |
| Unbounded alert flood or SMS cost path | Customer harm and business viability risk. |
| No tested backup/restore, release rollback, or support incident process | Team cannot recover responsibly. |
| Critical security assessment finding unresolved | Material compromise risk. |
| Customer claims/docs materially exceed tested capability | Trust and legal risk. |

## 21.2 Scope-cut order

First cut: breadth of device recognition, optional reports, push notifications, and cosmetic customization.

Second cut: advanced RTSP/frame freshness, unusual sequential-pattern detection, quiet-hour options, and nonessential admin convenience.

Do not cut: core heartbeat, offline replay, incident truthfulness, consent, tenant isolation, signed updates, readiness, dedupe, restoration, or release evidence.

# 22. Estimation and Capacity Planning Guidance

| Size | Interpretation | Planning action |
| --- | --- | --- |
| XS | Localized change with known pattern and limited test surface. | May be bundled only when acceptance remains independent. |
| S | Small story touching one bounded component with clear tests. | Normal sprint candidate. |
| M | Crosses component boundary or requires meaningful UX/test design. | Refine interfaces and acceptance before start. |
| L | Vertical capability, complex migration, security control, or broad failure matrix. | Split into demonstrable increments where possible. |
| XL | Too uncertain or broad for implementation. | Create spike and decompose; do not commit as one item. |

## 22.1 Estimation cautions

Relative sizes include implementation, tests, security/privacy work, observability, migration, documentation, and acceptance—not coding alone.

Integrations with Windows, SMS, billing, identity, camera protocols, and software signing carry external uncertainty.

Real-property testing and beta support require explicit capacity.

Do not convert these sizes into a fixed launch date until the R0 prototype and first internal-alpha soak produce evidence.

# 23. Backlog Governance and Change Control

| Decision type | Required record / approver |
| --- | --- |
| Move P0 out of target release | Product owner + technical lead + named risk consequence. |
| Change alert classification/language | Product owner + incident model owner; scenario tests updated. |
| Change local/cloud data boundary | Architecture + security/privacy review; customer notice impact assessed. |
| Add new privileged agent capability | ADR + threat-model update + security approval. |
| Change SMS consent/escalation behavior | Product + security/privacy + provider/compliance review. |
| Accept launch security/reliability defect | Founder + technical/security owner; severity, customer impact, mitigation, deadline documented. |
| Add feature to MVP | Must identify which existing scope or capacity it displaces; no silent expansion. |

## 23.1 Review cadence

Weekly delivery review: blockers, critical path, defects, acceptance evidence.

Release-boundary review: P0 completion, unresolved risks, operational readiness, customer language.

Monthly product review during beta: false/missed alerts, setup completion, support burden, SMS cost, retention, and requested features.

Immediate review after material security incident, bad update, cross-tenant concern, or missed critical notification.

# Appendix A — Master Story Index

| ID | Epic | Priority | Release | Size | Short title / outcome |
| --- | --- | --- | --- | --- | --- |
| DEL-001 | E0 | P0 | R0 | S | Create source repositories and protected main branch with required review. |
| DEL-002 | E0 | P0 | R0 | M | Establish local, test, staging, and production configuration boundaries. |
| DEL-003 | E0 | P0 | R0 | M | Build CI pipeline for compile, unit tests, linting, dependency scan, and artifact publication. |
| DEL-004 | E0 | P0 | R0 | M | Create database migration workflow for cloud and local schemas. |
| DEL-005 | E0 | P1 | R1 | S | Introduce feature flags and environment-scoped rollout controls. |
| DEL-006 | E0 | P1 | R1 | S | Adopt coding, logging, error-handling, and API review standards. |
| DEL-007 | E0 | P1 | R1 | S | Create Architecture Decision Record workflow and initial ADR register. |
| DEL-008 | E0 | P1 | R2 | M | Create signed release manifest and artifact provenance process. |
| AGT-001 | E1 | P0 | R0 | M | Implement Windows service host with structured startup, shutdown, and health state. |
| AGT-002 | E1 | P0 | R0 | M | Create install, repair, upgrade, and uninstall package. |
| AGT-003 | E1 | P0 | R0 | S | Configure automatic startup and bounded service recovery after crash. |
| AGT-004 | E1 | P0 | R1 | M | Implement local readiness/status interface for service, cloud, gateway, and monitoring state. |
| AGT-005 | E1 | P0 | R1 | M | Detect sleep/hibernation risk and guide the customer to an always-on configuration. |
| AGT-006 | E1 | P0 | R1 | M | Implement agent registration and secure credential bootstrap. |
| AGT-007 | E1 | P0 | R1 | M | Implement versioned configuration cache with transactional apply and last-known-good rollback. |
| AGT-008 | E1 | P1 | R2 | M | Implement staged, signed, rollback-capable automatic updates. |
| AGT-009 | E1 | P1 | R2 | S | Provide privacy-safe diagnostic bundle generation. |
| AGT-010 | E1 | P1 | R2 | S | Enforce CPU, memory, concurrency, and network-rate guardrails. |
| DAT-001 | E2 | P0 | R0 | M | Create versioned local SQLite schema for state, probe samples, events, config, and outbox. |
| DAT-002 | E2 | P0 | R0 | M | Implement transaction boundaries and crash-safe journal settings. |
| DAT-003 | E2 | P0 | R0 | M | Implement durable outbox for material events and heartbeat-adjacent evidence. |
| DAT-004 | E2 | P0 | R0 | S | Assign stable event IDs and monotonic agent sequence numbers. |
| DAT-005 | E2 | P0 | R1 | M | Implement reconciliation and cloud acknowledgment checkpoints. |
| DAT-006 | E2 | P0 | R1 | S | Implement UTC time handling, clock-skew detection, and observed-versus-received timestamps. |
| DAT-007 | E2 | P1 | R2 | S | Implement bounded local retention, compaction, and disk-pressure behavior. |
| DAT-008 | E2 | P0 | R1 | M | Protect local secrets using Windows-bound secure storage and strict ACLs. |
| DAT-009 | E2 | P1 | R2 | S | Create local backup/recovery procedure for configuration and durable evidence. |
| MON-001 | E3 | P0 | R0 | S | Identify active gateway and primary local interface. |
| MON-002 | E3 | P0 | R0 | M | Implement independent internet checks using multiple destinations and methods. |
| MON-003 | E3 | P0 | R0 | S | Implement explicit DNS resolution health check. |
| MON-004 | E3 | P0 | R1 | L | Discover LAN devices using safe bounded methods and merge observations into inventory. |
| MON-005 | E3 | P0 | R1 | M | Create durable device identity evidence across changing IP addresses. |
| MON-006 | E3 | P0 | R1 | M | Allow customer to create monitor targets and choose appropriate reachability/service checks. |
| MON-007 | E3 | P0 | R1 | M | Implement TCP/service reachability probes with deadlines and response bounds. |
| MON-008 | E3 | P1 | R2 | M | Recognize probable cameras, recorders, hubs, and infrastructure using evidence-based labels. |
| MON-009 | E3 | P1 | R2 | L | Prototype RTSP session/frame-freshness check without storing media content. |
| MON-010 | E3 | P0 | R1 | M | Implement baselines, confirmation windows, flapping suppression, and cooldowns. |
| MON-011 | E3 | P0 | R2 | M | Model dependency chain among internet, gateway, switch/hub, recorder, and cameras. |
| MON-012 | E3 | P1 | R2 | S | Generate new-device and identity-change events with customer controls. |
| CLD-001 | E4 | P0 | R0 | M | Implement organization, user, property, and agent persistence baseline. |
| CLD-002 | E4 | P0 | R0 | M | Implement one-time agent registration endpoint and credential issuance. |
| CLD-003 | E4 | P0 | R0 | M | Implement authenticated heartbeat ingestion with server receive timestamp. |
| CLD-004 | E4 | P0 | R0 | L | Implement heartbeat lease evaluator and property-silence state machine. |
| CLD-005 | E4 | P0 | R0 | L | Implement idempotent batch event ingestion and acknowledgment. |
| CLD-006 | E4 | P0 | R1 | M | Implement versioned configuration snapshot/delta delivery. |
| CLD-007 | E4 | P1 | R2 | M | Implement bounded command queue for safe agent actions such as refresh/test. |
| CLD-008 | E4 | P0 | R1 | M | Implement customer API conventions, errors, pagination, idempotency, and rate limits. |
| CLD-009 | E4 | P0 | R1 | M | Create dashboard read projections for property, agent, device, and incident status. |
| CLD-010 | E4 | P1 | R2 | M | Add background-job framework with tenant context, retries, and dead-letter visibility. |
| INC-001 | E5 | P0 | R0 | M | Implement canonical device/target health state machine. |
| INC-002 | E5 | P0 | R0 | M | Classify property silence from cloud lease expiry without overclaiming cause. |
| INC-003 | E5 | P0 | R0 | M | Classify local gateway, DNS, and internet failure combinations. |
| INC-004 | E5 | P0 | R1 | M | Classify isolated critical-device/service failure while upstream path remains healthy. |
| INC-005 | E5 | P0 | R1 | M | Correlate simultaneous multi-device failures into likely shared-dependency incident. |
| INC-006 | E5 | P1 | R2 | L | Detect unusual sequential critical-device failures as a pattern, not a criminal conclusion. |
| INC-007 | E5 | P0 | R1 | M | Assign evidence-based confidence and reason codes. |
| INC-008 | E5 | P0 | R1 | M | Implement incident open, update, acknowledge, restore, close, and revise lifecycle. |
| INC-009 | E5 | P0 | R1 | M | Correlate restoration evidence and calculate downtime without hiding uncertainty. |
| INC-010 | E5 | P0 | R2 | M | Build customer-safe evidence timeline projection. |
| INC-011 | E5 | P1 | R2 | S | Support planned maintenance/suppression without erasing evidence. |
| NTF-001 | E6 | P0 | R0 | M | Create versioned template system for open, update, restore, test, and uncertainty messages. |
| NTF-002 | E6 | P0 | R0 | M | Implement transactional email delivery and provider receipt processing. |
| NTF-003 | E6 | P0 | R0 | M | Implement SMS delivery with verified consent, STOP handling, quotas, and receipts. |
| NTF-004 | E6 | P0 | R1 | M | Implement per-incident deduplication, cooldown, and alert-flood suppression. |
| NTF-005 | E6 | P0 | R1 | M | Create trusted-contact enrollment, verification, role, and removal lifecycle. |
| NTF-006 | E6 | P0 | R1 | L | Implement escalation policies by severity, channel, delay, and unresolved duration. |
| NTF-007 | E6 | P1 | R2 | S | Implement quiet hours with emergency-severity override. |
| NTF-008 | E6 | P0 | R1 | S | Implement end-to-end notification test from each configured property. |
| NTF-009 | E6 | P1 | R2 | M | Add mobile/web push channel behind channel abstraction. |
| NTF-010 | E6 | P1 | R2 | S | Expose quota use, provider delay, and destination failure to customer/support. |
| UX-001 | E7 | P0 | R1 | M | Implement account creation, sign-in, password recovery, and session management. |
| UX-002 | E7 | P0 | R1 | S | Implement property creation with timezone, label, and monitoring purpose. |
| UX-003 | E7 | P0 | R1 | L | Create guided agent enrollment and installer handoff flow. |
| UX-004 | E7 | P0 | R1 | L | Create discovery review flow with names, types, confidence, and corrections. |
| UX-005 | E7 | P0 | R1 | M | Create critical-device selection and dependency-chain setup. |
| UX-006 | E7 | P0 | R1 | M | Create notification destination, trusted contact, and escalation setup. |
| UX-007 | E7 | P0 | R1 | M | Implement readiness checklist and protection-state model. |
| UX-008 | E7 | P0 | R1 | M | Build responsive property status dashboard. |
| UX-009 | E7 | P0 | R2 | L | Build incident detail and evidence timeline with acknowledgment. |
| UX-010 | E7 | P0 | R2 | M | Implement Away/Tamper Mode and planned-maintenance controls. |
| UX-011 | E7 | P1 | R2 | M | Provide uptime/outage report and export. |
| UX-012 | E7 | P0 | R2 | S | Meet responsive and accessibility baseline for critical workflows. |
| SEC-001 | E8 | P0 | R0 | S | Adopt threat model, data classes, trust boundaries, and secure coding checklist. |
| SEC-002 | E8 | P0 | R1 | M | Implement managed human identity with secure sessions and MFA-ready design. |
| SEC-003 | E8 | P0 | R0 | M | Implement per-agent identity, protected credentials, rotation, and revocation. |
| SEC-004 | E8 | P0 | R0 | S | Enforce TLS, certificate validation, secure headers, and secret-free logs. |
| SEC-005 | E8 | P0 | R1 | M | Implement server-side RBAC and property authorization. |
| SEC-006 | E8 | P0 | R1 | M | Create automated cross-tenant and IDOR regression suite. |
| SEC-007 | E8 | P0 | R2 | L | Implement code signing, SBOM, dependency policy, update signing, and protected release keys. |
| SEC-008 | E8 | P0 | R1 | M | Implement logging/data-minimization rules and sensitive-field redaction. |
| SEC-009 | E8 | P0 | R2 | M | Implement customer export, retention, property deletion, and account deletion workflows. |
| SEC-010 | E8 | P0 | R0 | M | Implement messaging consent, destination verification, throttling, and abuse controls. |
| SEC-011 | E8 | P1 | R2 | M | Add SAST, dependency, secret, container/IaC, and dynamic security scanning. |
| SEC-012 | E8 | P0 | R3 | L | Complete independent pre-launch security assessment and remediate launch blockers. |
| BIL-001 | E9 | P0 | R2 | M | Define plan/entitlement model separate from payment provider. |
| BIL-002 | E9 | P0 | R2 | M | Implement quotas for properties, critical devices, SMS, contacts, and retention. |
| BIL-003 | E9 | P0 | R3 | L | Integrate subscription checkout, renewal, cancellation, and webhook validation. |
| BIL-004 | E9 | P0 | R2 | M | Meter SMS and other billable usage with reconciliation. |
| BIL-005 | E9 | P1 | R3 | S | Implement grace period, downgrade, and cancellation behavior. |
| BIL-006 | E9 | P0 | R2 | M | Implement audited support/admin controls for plan corrections and account recovery. |
| QA-001 | E10 | P0 | R0 | M | Establish unit-test baseline for state machines, probe decisions, templates, and validation. |
| QA-002 | E10 | P0 | R0 | L | Create cloud/agent integration environment with disposable data and fake providers. |
| QA-003 | E10 | P0 | R0 | L | Build deterministic scenario runner with virtual clock and scripted evidence. |
| QA-004 | E10 | P0 | R1 | M | Create physical failure-injection checklist and evidence-capture template. |
| QA-005 | E10 | P0 | R1 | M | Automate Windows compatibility tests across supported editions/updates. |
| QA-006 | E10 | P0 | R2 | L | Run long-duration agent/cloud soak with network churn and intermittent provider failure. |
| QA-007 | E10 | P0 | R2 | L | Run fault-injection tests for database, queue, messaging, auth, clock, and restart failures. |
| QA-008 | E10 | P1 | R2 | M | Validate heartbeat/reconnect-storm performance and notification throughput. |
| QA-009 | E10 | P0 | R2 | M | Perform accessibility and responsive UX audit on critical flows. |
| QA-010 | E10 | P0 | R3 | L | Create signed release regression suite and launch evidence package. |
| OPS-001 | E11 | P0 | R0 | M | Implement structured logs with correlation IDs, tenant-safe fields, and redaction. |
| OPS-002 | E11 | P0 | R1 | L | Create service dashboards for heartbeat freshness, incident rates, queues, provider outcomes, and errors. |
| OPS-003 | E11 | P0 | R1 | M | Configure operational alerts with runbook links and anti-noise thresholds. |
| OPS-004 | E11 | P0 | R1 | M | Implement immutable audit events for security, support, contacts, billing, and configuration. |
| OPS-005 | E11 | P0 | R2 | L | Build restricted support console and privacy-safe diagnostic workflow. |
| OPS-006 | E11 | P1 | R3 | S | Publish service status and customer communication workflow. |
| OPS-007 | E11 | P0 | R2 | L | Implement backup, restore, queue replay, and disaster-recovery exercises. |
| OPS-008 | E11 | P0 | R2 | M | Create security/availability incident response playbooks and contact tree. |
| OPS-009 | E11 | P1 | R3 | M | Define messaging-provider degradation/fallback behavior. |
| OPS-010 | E11 | P0 | R2 | S | Create beta support triage, defect severity, and escalation process. |
| REL-001 | E12 | P0 | R1 | S | Define internal-alpha properties, hardware/network diversity, and test owners. |
| REL-002 | E12 | P0 | R2 | M | Create private-beta enrollment, informed consent, eligibility, and support expectations. |
| REL-003 | E12 | P0 | R2 | M | Instrument product success metrics and beta feedback loop. |
| REL-004 | E12 | P0 | R2 | M | Create customer help center, onboarding guide, troubleshooting, and limitations copy. |
| REL-005 | E12 | P0 | R3 | M | Prepare terms, privacy notice, messaging disclosures, acceptable use, and billing disclosures for counsel review. |
| REL-006 | E12 | P0 | R3 | M | Finalize packaging, plans, trial/grace rules, and customer-facing positioning. |
| REL-007 | E12 | P0 | R3 | L | Execute commercial-MVP launch readiness review. |
| REL-008 | E12 | P0 | R3 | S | Create release rollback, pause-enrollment, and emergency notification procedures. |
| REL-009 | E12 | P1 | R3 | S | Publish release notes and known limitations in customer-safe language. |
| REL-010 | E12 | P1 | R4 | S | Run post-launch review and re-prioritize parking lot from evidence. |

# Appendix B — Specification Traceability

| Epic | Primary approved sources | Most important release evidence |
| --- | --- | --- |
| E0 | Delivery Foundation & Engineering System — Architecture §§18, 21–22; Security §§12, 17; API §§21–23 | Controlled demonstration and accepted story evidence for E0 |
| E1 | Windows Agent Runtime, Installation & Lifecycle — Prototype §§6, 14; Architecture §§5, 19; Security §8 | Controlled demonstration and accepted story evidence for E1 |
| E2 | Local Persistence, Outbox & Offline Reconciliation — Prototype §8; Architecture §§5.5, 8; API §8; Security §8.4 | Controlled demonstration and accepted story evidence for E2 |
| E3 | Network Discovery, Device Identity & Health Monitoring — PRD §§6.2–6.5; Prototype §7; Architecture §12 | Controlled demonstration and accepted story evidence for E3 |
| E4 | Cloud Control Plane, Heartbeats & Configuration — Prototype §§9–10; Architecture §6; API §§14–17 | Controlled demonstration and accepted story evidence for E4 |
| E5 | Incident Classification, Correlation & Evidence — PRD §§7–9; Flows §§5–14; Architecture §10; API §11 | Controlled demonstration and accepted story evidence for E5 |
| E6 | Notifications, Trusted Contacts & Escalation — PRD §6.8; Flows §§9–13; Architecture §11; Security §11 | Controlled demonstration and accepted story evidence for E6 |
| E7 | Customer Onboarding, Dashboard & Incident Experience — PRD §9; User Flows §§1–18; Architecture §7 | Controlled demonstration and accepted story evidence for E7 |
| E8 | Security, Privacy, Identity & Supply Chain — Security Model §§8–22; Architecture §§13–14; API §20 | Controlled demonstration and accepted story evidence for E8 |
| E9 | Plans, Entitlements, Billing & Administrative Controls — Architecture §20; API §§10, 16.6; PRD §6.11 | Controlled demonstration and accepted story evidence for E9 |
| E10 | Quality Engineering, Failure Injection & Release Validation — Prototype §§16–20; Security §21; Architecture §25 | Controlled demonstration and accepted story evidence for E10 |
| E11 | Observability, Support Operations & Recovery — Architecture §§15, 17–18; Security §§16, 18–19 | Controlled demonstration and accepted story evidence for E11 |
| E12 | Beta, Commercial Readiness & Launch Management — PRD §§13–16; Prototype §§19–20; Security §22 | Controlled demonstration and accepted story evidence for E12 |

TRACEABILITY RULE When an implementation decision changes a behavior defined in an approved source document, update the source specification or record an explicit superseding ADR/product decision. The backlog must not silently rewrite product requirements.

# Appendix C — Release Gate Checklists

## C.1 R0 feasibility gate

Windows service starts automatically and survives controlled restart/crash.

Gateway/internet evidence is collected with bounded probes.

Agent sends authenticated heartbeat and queues events offline.

Cloud opens one property-silence incident after threshold and one restoration after return.

Email/SMS test and incident delivery are verified with consent and receipts.

Controlled demo is repeatable; no manual database edits required.

Go/no-go scorecard approves continued investment.

## C.2 R1 internal-alpha gate

Installer, enrollment, readiness, discovery, critical-device monitoring, and status dashboard work on controlled properties.

Sleep/power risk is visible; protection status cannot be falsely green.

Core failure matrix includes isolated camera/DVR and shared internet outage.

Agent resource use and local storage remain bounded in continuous operation.

Team has operational dashboards, alerts, and issue triage.

## C.3 R2 private-beta gate

Guided setup succeeds without engineer intervention for representative users.

Trusted contacts, verification, escalation, acknowledgment, restoration, and incident timeline are complete.

Security/privacy P0 controls and tenant regression tests pass.

Signed update/rollback, support bundle, backup/restore, soak/fault tests, and support workflow are exercised.

Beta consent, limitations, support expectations, and success metrics are ready.

## C.4 R3 commercial-MVP gate

Every P0 R3 story is accepted or explicitly removed from public commitment.

Independent security assessment launch blockers are resolved.

Plans, quotas, billing, grace/cancellation, and messaging costs are reconciled.

Terms/privacy/messaging/customer claims match actual implementation.

Release regression, rollback, incident response, disaster recovery, support staffing, and status communications pass.

Founder, product, technical, security, QA, and operations owners sign go/no-go record.

# Appendix D — Post-MVP Parking Lot

| Candidate | Why deferred from R3 | Evidence required before prioritization |
| --- | --- | --- |
| Native iOS/Android applications | High platform/support cost; web/SMS/email establish core value first. | Demand for persistent push/mobile workflows and retention impact. |
| Dedicated hardware watchdog | Requires supply chain, certification, support, cellular/UPS design. | Software demand, high computer-sleep failure rate, willingness to buy hardware. |
| Cellular fallback | Recurring carrier cost and hardware/eSIM complexity. | Customers losing primary internet need differentiated cause and continued reporting. |
| Broad ONVIF/RTSP camera-health matrix | Protocol/vendor variability and credential support burden. | Supported-camera cohort, measurable value beyond device reachability. |
| Video freeze/image-change analysis | Privacy, CPU, false positives, content handling. | Strong customer need and privacy-preserving local-only feasibility. |
| macOS/Linux consumer agent | Multiplies installer/lifecycle/support matrix. | Material addressable demand and team capacity. |
| MSP/installer multi-tenant console | Different permissions, billing, support, and delegated administration. | Installer channel traction and validated unit economics. |
| Router control/device blocking | Changes product category and risk profile. | Clear customer demand that outweighs security/support scope. |
| Parental controls/firewall/vulnerability scanner | Outside property-watchdog wedge and direct competition with mature products. | Separate product strategy, not MVP feature request. |
| Cloud video recording/dispatch | Major liability, storage, licensing, and operational change. | Independent business case and architecture/threat model. |

# Approval and Immediate Next Actions

| Action | Owner role | Output |
| --- | --- | --- |
| Approve release model and P0/P1/P2 definitions | Founder / product owner | Backlog baseline v0.1 approved. |
| Select implementation team and assign epic ownership | Founder / technical lead | Named owners and reviewer matrix. |
| Resolve R0 technology/provider choices | Technical lead | ADRs for Windows stack, cloud, identity, messaging, database, deployment. |
| Import backlog IDs into issue tracker | Delivery lead | Tracker with fields, dependencies, and source links. |
| Refine Wave 0 and Wave 1 items to Ready | Engineering + QA + security | First executable iteration backlog. |
| Build R0 vertical slice and run go/no-go review | Cross-functional team | Prototype evidence and revised estimates/risks. |
| Update this backlog after R0 evidence | Product + technical lead | v0.2 with decomposed stories, actual constraints, and beta plan. |

NEXT FORMAL DELIVERABLE After this backlog is approved, the remaining planned strategic deliverable is the Beta & Commercialization Plan v0.1. In parallel, engineering can begin refining Wave 0/Wave 1 stories and turning the feasibility specification into the first code repository.